## Recruitment plan
Example Recruitment Plan
This recruitment plan provides an example only and will need to be tailored to your charity's circumstances - including who to involve at each stage and to ensure it fits with the requirements of your governing document.
Process/activity | Who | Timescale - weeks
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Check governing document
Confirm number of trustees to recruit | Chair | bar: Timescale - weeks 1
Check process including 3rd party rights to nominate/appoint | Chair | bar: Timescale - weeks 1
Check notice periods for meetings | General or Governance Manager | bar: Timescale - weeks 1; Timescale - weeks 11
Planning recruitment
Key dates including meetings and notice periods | Governance Manager | Timescale - weeks 3: BoT; Timescale - weeks 13: BoT; Timescale - weeks 14: Notice for AGM; Timescale - weeks 17: AGM; Timescale - weeks 19: BoT
Agree who will be involved at each stage | Recruitment Group | bar: Timescale - weeks 1
Confirm stages in campaign and timescales | Recruitment Group | bar: Timescale - weeks 1
Work out what you need
Assess skills, experience and other qualities | Board of Trustees | bar: Timescale - weeks 2 to Timescale - weeks 3
Agree gaps based on what you have and challenges charity is facing | Board of Trustees | bar: Timescale - weeks 2 to Timescale - weeks 3
Produce person specification | Governance Manager | bar: Timescale - weeks 3 to Timescale - weeks 4
Get your advert out there
Write first draft of advert | General Manager and Chair | bar: Timescale - weeks 4
Decide where to advertise/target | General or Governance Manager | bar: Timescale - weeks 4; Timescale - weeks 8
Update advert and/or tailor to specific skills | General Manager | bar: Timescale - weeks 4 to Timescale - weeks 5
Produce recrutiment pack (if applicable) | Governance Manager | bar: Timescale - weeks 4 to Timescale - weeks 5
Approve recruitment materials and where to advertise | Recruitment Group | bar: Timescale - weeks 6; Timescale - weeks 8
Post your advert! | Admin team | bar: Timescale - weeks 6 to Timescale - weeks 10
Interview and selection
Agree interview questions | Chair, General Manager, external expert | bar: Timescale - weeks 9 to Timescale - weeks 10
Shortlist applicants | Chair and external expert | bar: Timescale - weeks 9 to Timescale - weeks 11
Arrange interviews | Governance Manager and admin team | bar: Timescale - weeks 11
Produce interview template for notes | Governance Manager | bar: Timescale - weeks 11
Hold interviews | Chair, trustee, external expert | bar: Timescale - weeks 12
Select candidates to recommend for appointment | Chair, trustee, external expert | bar: Timescale - weeks 12
Notify all candidates of outcome of interviews | Admin team | bar: Timescale - weeks 12
Take up references and confirm trustee eligibility | Governance Manager | bar: Timescale - weeks 12 to Timescale - weeks 13
Notify Board of Trustees; agreement to propose successful candidates | Board of Trustees, General Manager | bar: Timescale - weeks 13
Formal appointment and induction
Give notice to members (if applicable) including candidate biographies | Governance manager and admin team | bar: Timescale - weeks 14 to Timescale - weeks 16
Hold general meeting/trustee meeting to appoint trustees | Board of Trustees, Members | bar: Timescale - weeks 17
Send induction pack to new trustees | Governance manager and admin team | bar: Timescale - weeks 17
Arrange induction visit and meetings | Chair, General Managr | bar: Timescale - weeks 17
Follow-up with new trustees | Chair | bar: Timescale - weeks 20
Evaluate recruitment and induction | New trustee(s), Chair, General Manager | bar: Timescale - weeks 23

## Personnel
Who you involve in your recruitment campaign will depend on the people-resource you have available. Here are some examples of the people you might involve. The key is to agree at the outset who will be involved in each stage and ensure they will be available based on your timescales. The Board of Trustees should also approve who they will delegate to and what that group has authority to decide. For example, the Board may agree that a recruitment group will select suitable candidates but decide that the Board must give approval for those candidates to be proposed for election by the membership.
Chair | eg. Chair of the Board of Trustees or Chair of Nominations & Governance Committee if you have one
General Manager | eg. General/Office Manager, CEO, Senior member of staff
Governance Manager | eg. Head of Goverance, Company Secretary, Governance Manager, Governance Officer, Honorary Secretary
Recruitment group | eg. Nominations & Governance Committee if you have one or a short-term Task & Finish Group set up to oversee the recruitment process. Could include Chair, another trustee, General Manager, a volunteer or Governance Manager and/or an external expert
Board of Trustees | Board of Trustees
External expert(s) | Someone external to the charity that has specialist knowledge of the skill(s) you're trying to recruit
Admin team | eg. admin staff or a hub of volunteers that provide admin support
Members | The charity's members

## Summary
Process/activity | Timescale - weeks
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Check governing document
Planning recruitment |  |  | BoT | [9 empty] | BoT | Notice for AGM |  |  | AGM |  | BoT
Work out what you need
Get your advert out there
Interview and selection
Formal appointment and induction